## Summary
VaultChat -> WhatsApp Parity Task Plan
Scope: speed, data flow, storage, data fetching, UI elements, UX on the current locked stack (RN/Expo + libsignal-rn + Fastify/Socket.IO + PG17 + Redis/BullMQ + R2 + op-sqlite).
Total tasks:
By Priority
P0 - Launch blocking / do first
P1 - Pre-launch parity
P2 - Fast follow
P3 - Post-launch
By Category
Speed
Data Flow
Storage
Data Fetching
UI Elements
UX
By Track
Track A
Track E
Track F
Infra
Later
Status: Done | 33
% Complete | 29.5%
Recommended order: 1) All Track A P0 rows 2) Mumbai migration 3) Track E media pipeline 4) Retention decision + backup path 5) Track F (Status/E2EE UX) 6) P2/P3 fast-follows.
VERIFIED STATUS vs SOURCE (2026-07-09)
Done | 33
Partial | 57
Not Started | 22
Total | 112
See docs_latest/parity-status-vs-source.md for evidence + critical findings

## Tasks
ID | Category | Sub-Area | Task | Description / Acceptance Criteria | WhatsApp Reference Behavior | Priority | Effort | Track | Dependencies | Status | Evidence (file:line) | Gap / Notes | Verified
VC-001 | Speed | Transport | Diagnose Socket.IO transport in production | Log engine.io transport per connection; confirm % stuck on HTTP long-polling vs websocket. Capture upgrade failure reason. | Persistent binary TCP/TLS socket, always connected | P0 | S | Track A |  | Done | lib/socket.ts:83-95; lib/perf.ts:69-72 |  | 2026-07-09 vs source
VC-002 | Speed | Transport | Fix WebSocket upgrade path | Nginx/proxy must pass Upgrade/Connection headers; correct timeouts; client transports=['websocket'] with polling fallback only as last resort. Acceptance: >95% sessions on websocket. | N/A (native socket) | P0 | S | Track A | Diagnose transport | Done | lib/socket.ts:71; DEPLOY_HETZNER.md:150-156 | nginx conf lives in a deploy doc, not a committed .conf | 2026-07-09 vs source
VC-003 | Speed | Transport | Sticky sessions / single-origin socket routing | Ensure load balancer routes a session to one node, or move fanout to Redis adapter so any node can deliver. | Single logical connection per device | P0 | S | Track A |  | Done | vaultchat-backend/server.js:66-82; docker-compose.yml:102 |  | 2026-07-09 vs source
VC-004 | Speed | Transport | Redis pub/sub adapter for cross-instance fanout | socket.io-redis adapter so delivery works regardless of which node holds the recipient socket. | Server-side routing layer | P1 | M | Track A |  | Done | server.js:66-82 (@socket.io/redis-adapter); Kafka fanout server.js:119-128 |  | 2026-07-09 vs source
VC-005 | Speed | Transport | Fast reconnect with session resume token | Store auth credential; skip full re-auth on reconnect; target <1s reconnect on network switch. | Noise-pipes cached credential, instant resume | P1 | M | Track A |  | Partial | lib/socket.ts:73-77 (reconnect 500/5000) | No resume token; full JWT re-auth each reconnect (server.js:672-690); no connectionStateRecovery | 2026-07-09 vs source
VC-006 | Speed | Transport | Heartbeat/ping interval tuning for mobile | Tune pingInterval/pingTimeout for mobile radio wake cost vs dead-connection detection. | Optimized keepalive for 2G/3G | P2 | S | Track A |  | Done | server.js:57-58 (pingInterval/pingTimeout); lib/socket.ts:77 |  | 2026-07-09 vs source
VC-007 | Speed | Transport | Binary payload format (protobuf/msgpack) over WS | Replace JSON stanzas with compact binary schema; measure frame size reduction. | FunXMPP compact binary stanzas | P2 | L | Later | WebSocket fix | Not Started | default JSON parser server.js:55-60 | No msgpack/protobuf parser on either side | 2026-07-09 vs source
VC-008 | Speed | Send pipeline | Optimistic local insert on send | Insert message into op-sqlite with status=PENDING and render clock icon BEFORE any network I/O. UI must never await server. | Core WhatsApp pattern: UI never waits on network | P0 | M | Track A |  | Done | app/chat.tsx:806-824; lib/messageQueue.ts:100-106 | Queue persisted in AsyncStorage, not sqlite (functionally equivalent) | 2026-07-09 vs source
VC-009 | Speed | Send pipeline | Client-generated message IDs | UUID/ULID generated on device; server treats as idempotency key for dedup on retry. | Client-generated key_id | P0 | S | Track A |  | Done | messageQueue.ts:74-76,144-147; routes/chats.js:734-853 | Done (fixed 2026-07-10, pending deploy: migration 055 + client_id idempotency) | FIXED 2026-07-10
VC-010 | Speed | Send pipeline | Persisted client outbound queue + backoff | Unsent messages survive app kill; exponential backoff retry when socket restored. | Local DB outbound queue, socket-independent | P0 | M | Track A | Client message IDs | Done | messageQueue.ts:24-27 (backoff), 211-228 (drain on boot/NetInfo/periodic) |  | 2026-07-09 vs source
VC-011 | Speed | Send pipeline | Server ack -> SENT tick state machine | Distinct states PENDING/SENT/DELIVERED/READ driven by ack + receipt stanzas; per-state UI ticks. | Single tick on server ack, queue delete on delivery | P0 | M | Track A |  | Done | app/chat.tsx:3506-3517,3868-3875; migrations/006_delivery.sql:12-13 |  | 2026-07-09 vs source
VC-012 | Speed | Infra | Mumbai VPS migration | Move app+DB+coturn to Mumbai region; measure RTT from Indian ISPs before/after. | Global edge presence | P0 | L | Infra |  | Not Started | Hetzner/Finland: docker-compose.yml:107; constants/server.ts:9 | No ap-south (Mumbai) region for app+DB+coturn | 2026-07-09 vs source
VC-013 | Speed | Infra | Media edge locality (R2/CDN) for India | Verify R2 access latency from India; add Cloudflare cache rules for ciphertext blobs. | CDN-stored media blobs | P1 | S | Infra |  | Partial | S3-compatible storage lib/storage.js:1-2,91-95 | No Cloudflare CDN/cache rules; no India edge; staging on MinIO | 2026-07-09 vs source
VC-014 | Speed | Infra | DB indexes for hot paths | Indexes on messages(chat_id,sort_ts), receipts(msg_id), chats(sort_timestamp). EXPLAIN ANALYZE top queries. | N/A (queue model) | P1 | S | Track A |  | Partial | migrations/002_chats.sql:72 messages(chat_id,id DESC); :29 chats(last_message_at) | No receipts(msg_id) index (no receipts table); no dedicated sort_ts column | 2026-07-09 vs source
VC-015 | Speed | Infra | PgBouncer pool + Fastify tuning | Transaction pooling mode, pool sizing, keepalive; load test message insert path. | Erlang massive concurrency | P1 | S | Infra |  | Partial | PgBouncer 6432 DEPLOY_HETZNER.md:59-62; db.js:1-8 | Backend is Express not Fastify; PgBouncer is ops-only (no compose service) | 2026-07-09 vs source
VC-016 | Speed | Client render | Cold start renders from local DB first | App open shows chat list + last messages from op-sqlite instantly; socket connect happens after first paint. | Chat list renders with zero network | P0 | M | Track A |  | Done | app/(tabs)/chats.tsx:102-107; app/chat.tsx:400-401 (paint cache before network) |  | 2026-07-09 vs source
VC-017 | Speed | Client render | Cursor-based local message pagination | Load newest N messages; page older on scroll from local DB only. | Paged cursor over msgstore | P1 | M | Track A |  | Partial | app/chat.tsx:1629 getMessages({before:oldest}) | Older pages fetched from SERVER, not local DB; localDb has no before-cursor query | 2026-07-09 vs source
VC-018 | Speed | Client render | Inverted list perf (FlashList) + memoized bubbles | Stable keys, memoized bubble components, no re-render storms on receipt updates. | Native RecyclerView efficiency | P1 | M | Track A |  | Partial | app/chat.tsx:2033 FlatList; MemoBubble 2058; keyExtractor 2036 | Uses tuned FlatList; @shopify/flash-list not in repo | 2026-07-09 vs source
VC-019 | Speed | Client render | Hermes + startup profiling | Enable/verify Hermes, inline requires, measure TTI on low-end Android. | Native app startup | P2 | M | Later |  | Done | app.json:11 jsEngine=hermes; lib/perf.ts; app/perf-debug.tsx | Inline requires rely on Metro defaults | 2026-07-09 vs source
VC-020 | Speed | Media speed | Embedded micro-thumbnail in message payload | Tiny blurred preview bytes inside E2EE message so bubbles render instantly before download. | Micro-thumbnail travels in message | P1 | M | Track A |  | Done | lib/sendMedia.ts:64-66,94-96; lib/thumbnails.ts:23-42; render chat.tsx:3287-3289 |  | 2026-07-09 vs source
VC-021 | Speed | Media speed | Compression profiles (Standard/HD) | Standard ~1600px / HD ~4096px image tiers; video bitrate tiers; user toggle at compose. | Upload quality setting | P1 | M | Track E |  | Not Started | no resize/bitrate tiers in sendMedia.ts / mediaAttachments.ts | No 1600/4096 image tiers, no video bitrate tiers, no compose-time quality toggle | 2026-07-09 vs source
VC-022 | Speed | Media speed | Progressive video playback from partial file | Play while downloading; chunked write to local file. | Streamed chunk decrypt/playback | P2 | M | Later |  | Not Started | app/chat.tsx:3316-3336 full download then play | No play-from-partial-file / progressive streaming | 2026-07-09 vs source
VC-023 | Speed | Presence | Subscribe-on-open presence model | Only subscribe to a peer's presence while their chat is open; unsubscribe on exit. Avoid global presence fanout. | Presence subscription per open chat | P1 | S | Track A |  | Not Started | global presence_changed app/chat.tsx:553-558,622 | No per-peer subscribe-on-open / unsubscribe-on-exit | 2026-07-09 vs source
VC-024 | Speed | Presence | Typing indicator throttling | composing stanza max 1 per N sec + paused after idle; never persisted. | Throttled chatstate stanzas | P2 | S | Track A |  | Done | app/chat.tsx:750-764 (edge-triggered typing_start + idle stop, never persisted) |  | 2026-07-09 vs source
VC-025 | Data Flow | Receipts | Delivered receipt stanza + routing | Recipient device sends delivered receipt immediately after persist; routed to sender; updates tick. | receipt(delivered) per device | P0 | M | Track A |  | Done | app/chat.tsx:494-495 markDelivered; routes/chats.js:1014-1035 broadcast | Only fires while that chat screen is open | 2026-07-09 vs source
VC-026 | Data Flow | Receipts | Read receipt batching + privacy toggle | Batch read receipts on chat open; suppress both directions if either side disabled receipts. | Blue ticks, reciprocity rule | P0 | M | Track A |  | Done | app/chat.tsx:698-709 debounced markRead; toggle col migrations/009_blocks.sql:26 | Done (fixed 2026-07-10, pending deploy: read-receipt reciprocity, server-enforced) | FIXED 2026-07-10
VC-027 | Data Flow | Receipts | Per-(user,device) receipts schema | Receipts table keyed by (message, user, device) so multi-device later is a migration not rewrite. | receipt_user/receipt_device tables | P0 | S | Track A |  | Not Started | migrations/006_delivery.sql:8-10 'Per-USER, not per-device'; 002_chats.sql:42 | Receipts are per-user pointers on chat_members; devices table ignored -> multi-device = rewrite | 2026-07-09 vs source
VC-028 | Data Flow | Receipts | Played receipt for voice notes | Separate receipt type; blue mic UI on sender side. | Played receipt stanza | P2 | S | Later |  | Not Started | no played receipt type/column anywhere | No played receipt, no blue-mic UI | 2026-07-09 vs source
VC-029 | Data Flow | Message ops | Delete-for-everyone (revoke) | Revoke message referencing target ID; receivers blank to tombstone; enforce time window. | Revoke within window; tombstone bubble | P1 | M | Track A |  | Done | routes/chats.js:987-1002 soft-delete; tombstone app/chat.tsx:3584-3587 | Fixed 2026-07-11: revoke window enforced server-side (2d12h, WhatsApp parity) + client hint; legacy edit/delete socket relays removed | FIXED 2026-07-11
VC-030 | Data Flow | Message ops | Edit message flow | Edit as new E2EE message referencing original; 15-min window; receiver replaces text, keeps ID, shows Edited tag. | Edited tag mechanics | P2 | M | Later |  | Done | lib/chatService.ts:622-627; 15-min window routes/chats.js:62,971; 'edited' tag chat.tsx:3859 | In-place PATCH rather than a new referencing message (same outcome) | 2026-07-09 vs source
VC-031 | Data Flow | Message ops | Reactions as reference messages | Tiny E2EE message referencing target; client aggregates counts; reactor list view. | message_add_on model | P1 | M | Track A |  | Done | getReactionCounts chatService.ts:1276-1282; listReactors :1272-1274 | Fixed 2026-07-11: reactions are E2EE reference messages ({reactsTo,op,emoji} sealed in content, meta null); client aggregates, one-per-user WhatsApp model; server side-effects guarded; legacy plaintext endpoints kept read-only for old builds | FIXED 2026-07-11
VC-032 | Data Flow | Message ops | Quoted reply with snapshot | Reply embeds quoted ID + content snapshot; tap scrolls to original via local lookup. | Quoted bubble + jump | P1 | M | Track A |  | Partial | replyToId chatService.ts:564,577; local resolveReply chat.tsx:361-363; jump 1648-1673 | No content snapshot embedded; renders 'Tap to view' if original not cached locally | 2026-07-09 vs source
VC-033 | Data Flow | Message ops | Forward metadata + limits | Carry forward-count; show Forwarded / Forwarded many times; enforce 5-chat / 1-chat limits. | Anti-viral forward limits | P2 | S | Later |  | Partial | meta.forwardedFrom chatService.ts:1288-1297; label chat.tsx:3684 | No forward-count, no 'Forwarded many times', no 5-chat/1-chat limits | 2026-07-09 vs source
VC-034 | Data Flow | Message ops | Mentions metadata + mute bypass | @mention JIDs in payload; mentioned user notified even in muted group. | Mention notification override | P1 | S | Track A |  | Done | meta.mentions chat.tsx:804-805; mute bypass routes/chats.js:131-146 |  | 2026-07-09 vs source
VC-035 | Data Flow | Groups | Sender Key distribution on join | Distribute sender key via pairwise Signal sessions once per member; one ciphertext per group message after. | Sender Keys architecture | P0 | M | Track F |  | Done | services/crypto/groupSession.rn.ts:60-72 SKDM over pairwise ratchet; migrations/040_group_sender_keys.sql |  | 2026-07-09 vs source
VC-036 | Data Flow | Groups | Sender Key rotation on member removal | All members generate+redistribute new sender keys when anyone leaves/removed. Acceptance test: departed member cannot decrypt post-leave traffic. | Membership-level forward secrecy | P0 | M | Track F | Sender Key distribution | Done | groupSession.rn.ts:80-88 rotate+redistribute on removal; departed filtered :54-57 | Rotation is lazy (on next send), not eager on the removal event | 2026-07-09 vs source
VC-037 | Data Flow | Groups | Group blue-tick aggregation | Read state = ALL members read; per-member receipt rollup in Message Info. | All-member read requirement | P2 | S | Later |  | Done | per-member rollup app/chat.tsx:2373-2410 | Done (fixed 2026-07-10: blue tick = ALL current recipients) | FIXED 2026-07-10
VC-038 | Data Flow | Server queue | Per-device offline queue, delete on delivery | BullMQ/PG job deletes ciphertext row once device acks; TTL expiry ~30 days for undelivered. | Store-and-forward, delete on delivery | P0 | M | Track A |  | Partial | server.js:168-227 sweepDeliveredMessages + DOD_MAX_DAYS | Per-user not per-device; DELETE_ON_DELIVERY off by default; TTL default 0 = never (not 30d) | 2026-07-09 vs source
VC-039 | Data Flow | Server queue | Retention model decision + policy doc | Choose queue-only vs encrypted mailbox; document in privacy policy; drives backup requirements. | Queue-only (privacy asset) | P0 | S | Track A |  | Partial | server.js:168-183 comments; migrations/044_attachment_retention.sql | No standalone retention/privacy policy doc; decision only in code comments | 2026-07-09 vs source
VC-040 | Data Flow | Push | FCM high-priority data doorbell | Content-free push wakes app -> socket connect -> queue drain. Never put message content in push payload. | FCM as doorbell only | P0 | M | Track A |  | Done | calls doorbell routes/calls.js:57-89; VaultCallMessagingService.kt:63-69 | Fixed 2026-07-11: message push is a content-free doorbell — data-only FCM to fcm_token devices (native local notification, name from on-device directory), generic Expo fallback for others; channel post push genericized too | FIXED 2026-07-11
VC-041 | Data Flow | Push | No-GMS fallback: foreground-service socket | Persistent notification + socket for devices without Play Services (incl. your P30 Pro); battery-exemption onboarding. | WhatsApp maintains own socket on Huawei | P0 | L | Track A |  | Partial | batteryOptimization.ts:36-153; CallForegroundService.kt | Foreground service is CALL-ONLY; no persistent message socket, no Play-Services detection/fallback | 2026-07-09 vs source
VC-042 | Data Flow | Push | HMS Push Kit integration (Huawei) | Native doorbell for Huawei EMUI/HarmonyOS users. | N/A (WA uses own socket) | P2 | M | Later |  | Not Started | no HMS/Push Kit references anywhere | No HMS SDK/agconnect/token | 2026-07-09 vs source
VC-043 | Data Flow | Push | iOS APNs + NSE decrypt pipeline | Notification Service Extension pulls, decrypts, rewrites notification locally. | APNs + NSE model | P2 | L | Later |  | Not Started | generic Expo push lib/push.ts; voip modes withVaultChatCalls.js:158-167 | No Notification Service Extension target, no APNs decrypt pipeline | 2026-07-09 vs source
VC-044 | Data Flow | Identity | Contact discovery via hashed sync | Normalize + HMAC address book numbers; server matches registered users; populate local contacts mirror. Reuse existing HMAC-SHA256 lookup pattern. | Contact discovery service + wa.db | P0 | M | Track A |  | Done | routes/contacts.js:26-72; client hash lib/chatService.ts:1320-1360 | Fixed 2026-07-11: server-side pepper HMAC(pepper, sha256(digits)) on all 5 hash sites + /contacts/match peppers client hashes (echoes original); one-off backfill script scripts/pepper-phone-hash-backfill.js (self-gating) also seals legacy plaintext phone into phone_cipher | FIXED 2026-07-11
VC-045 | Data Flow | Identity | Push name in message envelope | Sender display name rides in payload; receivers without contact see it; cached locally. | Push name piggyback | P1 | S | Track A |  | Partial | sender name only in push title routes/chats.js:172,179 | No pushName field in the message envelope; receivers resolve from local contacts | 2026-07-09 vs source
VC-046 | Data Flow | Identity | Security-code-changed notices | On peer re-registration, show system bubble (setting-gated); block auto-resend until keys refetched. | Key change notification | P1 | M | Track F |  | Partial | manual verify: services/security/safetyNumber.ts; app/verify-contact.tsx | No automatic identity-key-change detection, no system bubble, no auto-resend block | 2026-07-09 vs source
VC-047 | Data Flow | Identity | Prekey directory + one-time prekey replenishment | Server stores identity/signed/one-time prekeys per device; client tops up pool when low; X3DH fetch endpoint. | Key directory service | P0 | M | Track A |  | Done | migrations/011_prekeys.sql; routes/user.js:1256-1401 X3DH + atomic OTPK consume; top-up e2eeSession.ts:181 | Keys are per-user (identity_keys PK=user_id), not per-device | 2026-07-09 vs source
VC-048 | Data Flow | Privacy | Server-side privacy gating (last seen/photo/about) | Enforce visibility rules on server, not client; block list stops delivery+presence+status. | Server-enforced privacy flags | P1 | M | Track A |  | Partial | last-seen server.js:465-471; block stops delivery chats.js:143-145; stories.js:55-71 | 'About' not gated; profile_photo_visible column unused in /chats fanout; broadcastPresence ignores blockers | 2026-07-09 vs source
VC-049 | Data Flow | Media | Random media key + HKDF encrypt + R2 upload | Per-file 32B key; AES-256-GCM ciphertext to R2; server never sees plaintext; hashes computed. | Media key model (CBC+HMAC legacy) | P0 | M | Track E |  | Partial | 32B key + AES-256-GCM lib/mediaCrypto.ts:20-41; opaque upload mediaAttachments.ts:21-38 | NO CONTENT HASHES computed (only the GCM auth tag provides integrity) | 2026-07-09 vs source
VC-050 | Data Flow | Media | Media message carries URL+key+hashes in E2EE envelope | Receiver fetches ciphertext, verifies hash/MAC, decrypts locally. | Key inside Signal envelope | P0 | M | Track E | Media key model | Partial | key rides in E2EE content mediaAttachments.ts:115-132 | Envelope carries key only - no URL (attachmentId sits in plaintext meta) and no hashes; no pre-decrypt verify | 2026-07-09 vs source
VC-051 | Data Flow | Media | Forward media without re-upload | Re-send same URL+key in new envelope; no second upload; saves data + R2 ops. | Forward optimization | P1 | S | Track E |  | Done | forwardMessage chatService.ts:1288-1298 re-sends same content+attachmentId, no re-upload |  | 2026-07-09 vs source
VC-052 | Data Flow | Media | Sender-generated link previews | Compose-time fetch renders title/desc/thumb into encrypted payload; receiver never touches URL. | Privacy-preserving link previews | P1 | S | Track A |  | Done | components/LinkPreview.tsx:20-37 - EVERY client (incl. receiver) fetches OG at render | Fixed 2026-07-11: sender-generated E2EE previews — sender device fetches OG + embeds title/desc/thumbnail-BYTES inside the E2EE payload (lib/linkPreview.ts wrap/unwrap); receiver renders from payload, never fetches; compose-time card above composer; legacy messages keep server-proxied fallback | FIXED 2026-07-11
VC-053 | Data Flow | Status | Status sender-key fanout to audience list | Privacy setting defines fanout set; media as encrypted blob; 24h client+server expiry; view receipts. | Status = sender-key E2EE stories | P1 | L | Track F |  | Done | lib/storyKeys.ts; status.tsx:212-218; stories.js:55-71,277-290; 24h expiry server.js:369-380 | Uses per-viewer key wrapping via 1:1 ratchet rather than a shared sender-key fanout | 2026-07-09 vs source
VC-054 | Data Flow | Calls | E2EE call signaling + SRTP keys in envelope | Offer/answer/ICE over chat socket as E2EE messages; SRTP master secret exchanged E2EE; relay sees ciphertext only. | E2EE signaling model | P1 | L | Later |  | Partial | plaintext socket events app/videocall.tsx:325-353; SDP in push routes/calls.js:77 | 2026-07-11: 1:1 call signaling now E2EE — per-call AES-256-GCM key ratchet-wrapped once (lib/callCrypto.ts); offer/answer/ICE sealed; SDP stripped from FCM push. Group calls remain plaintext (SFU work). | FIXED 2026-07-11
VC-055 | Data Flow | Calls | Always-relay privacy toggle | Force TURN relay to hide user IP from peer. | Call relay option | P2 | S | Later |  | Not Started | app/videocall.tsx:288-292 no iceTransportPolicy | No always-relay/force-TURN toggle to hide IP | 2026-07-09 vs source
VC-056 | Storage | Local DB | Full op-sqlite message schema | Tables: chat, message, message_media, quoted, mentions, reactions, receipts, call_log, group_participant, drafts. Mirror WhatsApp satellite-table design. | msgstore.db schema | P0 | M | Track A |  | Not Started | lib/localDb.ts:61-86 only messages/chats/sync_cursor | Missing message_media, quoted, mentions, reactions, receipts, call_log, group_participant, drafts | 2026-07-09 vs source
VC-057 | Storage | Local DB | At-rest DB encryption (SQLCipher) | SQLCipher-enabled op-sqlite; wrapping key in Android Keystore / iOS Keychain. | Encrypted msgstore + Keystore | P1 | M | Track F |  | Partial | field-level AES-GCM lib/cacheCrypto.ts:50-90; DEK sealed under PIN | Not SQLCipher (no whole-DB page encryption); only content/meta/data columns; gated off by VAULT_CACHE_ENCRYPTED | 2026-07-09 vs source
VC-058 | Storage | Local DB | FTS5 full-text index on messages | Sync FTS table on insert/edit/delete; powers global + in-chat search offline. | message_ftsv2 | P1 | M | Track A |  | Not Started | lib/localDb.ts:188-210 JS substring scan capped at 5000 rows | No FTS5 virtual table, no insert/edit/delete sync triggers | 2026-07-09 vs source
VC-059 | Storage | Local DB | Per-chat draft persistence | Save composer text on exit; red Draft prefix in chat list preview. | Draft store | P2 | S | Later |  | Done | lib/drafts.ts:18-48; 'Draft:' prefix app/(tabs)/chats.tsx:583 | Stored in AsyncStorage rather than a sqlite drafts table | 2026-07-09 vs source
VC-060 | Storage | Local DB | Signal protocol store on op-sqlite | Sessions, identity keys, prekeys, sender keys, trusted identities via libsignal-rn store interface. | axolotl.db | P0 | M | Track A |  | Partial | services/crypto/e2eeSession.ts:65-99 identity+sessions; senderKey.ts | Store is a KVStore over SecureStore, NOT op-sqlite; no trusted-identities store | 2026-07-09 vs source
VC-061 | Storage | Media files | Media directory structure + gallery visibility | Images/Video/Voice/Docs/Stickers dirs, Sent subfolders, media-visibility toggle (.nomedia). | Scoped storage layout | P2 | S | Later |  | Partial | lib/mediaStore.ts:34-45 dirs + Sent subfolders; pathFor :114-119 | No .nomedia toggle - code forces gallery visibility via RNFS.scanFile (:178) | 2026-07-09 vs source
VC-062 | Storage | Media files | Thumbnail + partial-download cache | Cache dir for thumbs and in-progress transfers; eviction policy. | Cache directory | P1 | S | Track E |  | Partial | thumbnails.ts:23-42; .Thumbs cache mediaStore.ts:81-95 | No eviction policy; no partial-download cache (getMedia downloads whole file) | 2026-07-09 vs source
VC-063 | Storage | Media files | Storage manager screen | Aggregate size per chat/file type from media table; bulk delete flows. | Manage storage | P3 | M | Later |  | Done | app/storage-manager.tsx:49-70 size by type; per-chat via localDb.ts:216-228; bulk delete :63-66 |  | 2026-07-09 vs source
VC-064 | Storage | Server | Delivered-ciphertext deletion job | BullMQ job hard-deletes queued ciphertext on device ack; TTL sweep for expired. | Delete-on-delivery | P0 | S | Track A | Retention decision | Done | server.js:184-227 sweepDeliveredMessages; :151-166 TTL sweepExpiredMessages | Env-gated (DELETE_ON_DELIVERY) off by default | 2026-07-09 vs source
VC-065 | Storage | Server | Media blob lifecycle on R2 | Retention window for ciphertext blobs (forwards/late downloads); GC job; dedupe by ciphertext hash. | CDN blob retention + GC | P1 | M | Track E |  | Partial | server.js:240-278 sweepDeliveredAttachments + MEDIA_TTL_DAYS; migrations/044 | No dedupe by ciphertext hash | 2026-07-09 vs source
VC-066 | Storage | Backup | Local encrypted backup file | Rolling local snapshots of message DB (crypt-file equivalent), last ~7 days. | msgstore.db.crypt15 | P1 | M | Later |  | Done | lib/cloudBackup.ts:188-213 writeLocalBackup, KEEP_LOCAL=7, pruneLocalBackups |  | 2026-07-09 vs source
VC-067 | Storage | Backup | Cloud backup + E2E passphrase wrap | User passphrase or 64-digit key wraps backup key; without it backup unreadable by anyone. Mandatory if queue-only retention chosen. | E2E encrypted backup, HSM vault | P1 | L | Later | Retention decision | Partial | lib/cloudBackup.ts:115-147; buildEncryptedBackup :51-85 AES-256-GCM | Backup key is ACCOUNT-MANAGED (fetched from /user/backup/key) - no user passphrase / 64-digit key wrap | 2026-07-09 vs source
VC-068 | Storage | Backup | QR device-to-device chat transfer | Local Wi-Fi encrypted transfer of DB+media between old and new phone. | Chat history transfer | P2 | L | Later |  | Not Started | app/vaultbeam.tsx P2P file transfer over WebRTC | Not QR, not local Wi-Fi discovery, transfers files not chat history | 2026-07-09 vs source
VC-069 | Storage | Multi-device | Per-device identity schema (design now) | Account -> devices(list) -> per-device sessions & queues & receipts. Schema in place even if single-device at launch. | Device IDs + client fanout | P0 | S | Track A |  | Not Started | migrations/005_devices.sql:13-23 devices = push tokens only | No account->device->session/queue/receipt graph; sessions+receipts are per-user | 2026-07-09 vs source
VC-070 | Storage | Multi-device | App-state sync mutation log (future) | E2EE append-only log for mute/pin/archive/star across own devices. | LT-hash app state sync | P3 | L | Later |  | Not Started | pin/archive are plain server columns migrations/012_pin_archive.sql | No E2EE append-only app-state mutation log | 2026-07-09 vs source
VC-071 | Data Fetching | Cold open | Cold-open sequence orchestration | Order: render local -> socket connect -> presence available -> drain queue -> decrypt+persist -> notify -> media per rules -> receipts out. | Documented cold-open sequence | P0 | M | Track A |  | Partial | pieces exist: chat.tsx local render; socket.ts; messageQueue.ts:212-228 initQueue | No single orchestrated cold-open pipeline enforcing the ordered sequence | 2026-07-09 vs source
VC-072 | Data Fetching | Queue drain | Ordered queue drain + out-of-order decrypt handling | Process stanzas in order; Double Ratchet skipped-message-key cache for out-of-order. | Skipped key cache | P0 | M | Track A |  | Done | services/crypto/e2ee.ts:184-288 MKSKIPPED skipped-key cache, MAX_SKIP=1000; ordered drain messageQueue.ts:171-207 |  | 2026-07-09 vs source
VC-073 | Data Fetching | Media | Auto-download matrix (network x type) | Settings grid: mobile/WiFi/roaming x photo/audio/video/docs; download button overlay when off. | Auto-download settings | P1 | M | Track E |  | Partial | lib/mediaPrefs.ts:10-36 global always/wifi/never + shouldAutoDownloadNow | Not a matrix - no per-type (photo/audio/video/doc) and no roaming dimension | 2026-07-09 vs source
VC-074 | Data Fetching | Media | Resumable chunked upload/download | Range requests to R2; resume after network drop; verify hash on completion. | Resumable chunked transfer | P1 | M | Track E |  | Partial | lib/transferManager.ts:87-97 resume, :142-155 sha256 verify (P2P only) | No HTTP range requests; media getMedia is a plain full download with no resume | 2026-07-09 vs source
VC-075 | Data Fetching | Profiles | Profile photo versioning + cache invalidation | Version hash per photo; clients re-fetch only on version bump notification. | Photo version hashes | P2 | S | Later |  | Not Started | routes/user.js:461 photo_url is a plain string | No version hash, no cache-busting, no refetch-on-bump | 2026-07-09 vs source
VC-076 | Data Fetching | Search | Global + in-chat local search UX | FTS-backed, filter chips (media/links/docs), in-chat hit navigation + jump-to-date. Zero server involvement. | Local-only search | P1 | M | Track A | FTS5 index | Partial | app/search.tsx global; app/in-chat-search.tsx; jump via setPendingJump | Not FTS-backed (JS substring); no filter chips; no jump-to-date | 2026-07-09 vs source
VC-077 | Data Fetching | Search | Semantic search layer (sqlite-vec) | Multilingual embeddings after FTS ships; on-device only. Differentiator beyond WhatsApp. | N/A (VaultChat advantage) | P3 | L | Later | Local search | Not Started | no sqlite-vec / embeddings anywhere | On-device semantic search absent | 2026-07-09 vs source
VC-078 | Data Fetching | Stickers/GIF | GIF/sticker search via server proxy | Proxy Giphy/Tenor so user IP is not exposed to provider; local recents cache. | GIF proxy | P2 | M | Track E |  | Partial | vaultchat-backend/routes/gif.js:1-52 GIPHY proxy (hides user IP) | No local recents cache in stickers.tsx / GifPicker.tsx | 2026-07-09 vs source
VC-079 | UI Elements | Chat list | Chat row full anatomy | Avatar, name resolution chain (contact->push name->number), typed preview with icons, You: prefix, ticks, timestamp humanization, unread badge, mute/pin icons. | Chat list row spec (doc sec 2.4) | P0 | M | Track A |  | Done | app/(tabs)/chats.tsx:544-591 (avatar/preview/You:/ticks/timestamp/unread/mute+pin) | Name chain simplified to peerName¦¦name; no push-name -> number fallback | 2026-07-09 vs source
VC-080 | UI Elements | Chat list | Typing/recording preview override | Live green 'typing... / recording audio...' swap while composing stanza active. | Preview override | P1 | S | Track A |  | Partial | app/(tabs)/chats.tsx:570-571 'typing...' override | No 'recording audio...' override | 2026-07-09 vs source
VC-081 | UI Elements | Chat list | Filter chips row | All / Unread / Favourites / Groups / custom lists; local queries. | Filter chips | P2 | S | Later |  | Partial | chats.tsx:38-44 FOLDERS All/Unread/Groups/Pinned/Archive; chips :342-356 | No Favourites chip, no custom user-defined lists | 2026-07-09 vs source
VC-082 | UI Elements | Chat list | Archived row + keep-archived setting | Collapsed archived count row; toggle controls un-archive on new message. | Archive behavior | P2 | S | Later |  | Partial | chats.tsx:285 archive chip; swipe-archive :535-537 | No dedicated Archived header row; no keep-archived setting | 2026-07-09 vs source
VC-083 | UI Elements | Chat list | Swipe + long-press chat actions | Archive, pin (max 3), mute, mark read/unread, delete, block, lock. | Row actions | P1 | M | Track A |  | Partial | chats.tsx:523-542 swipe pin/mute/archive/delete; :390 long-press multiselect | Pin not capped at 3; no mark read/unread; no lock; no block in swipe/bulk | 2026-07-09 vs source
VC-084 | UI Elements | Chat screen | Header with live presence subtitle | online / last seen / typing driven by subscription; group member list line. | Presence subtitle | P1 | M | Track A |  | Done | app/chat.tsx:1787-1793 online/last-seen/group members; typing 2139-2148 | Typing rendered above composer rather than in the subtitle | 2026-07-09 vs source
VC-085 | UI Elements | Chat screen | Text bubble rich rendering | Markdown (*_~```), linkify URLs/numbers, large-emoji rule (1-3 emoji). | Text bubble spec | P1 | M | Track A |  | Partial | app/chat.tsx:2742-2771 URL linkify; 2700-2713 mention coloring | NO markdown parsing (*_~``` inserted but never rendered); no phone linkify; no large-emoji (1-3) rule | 2026-07-09 vs source
VC-086 | UI Elements | Chat screen | All media bubble types | Image/video/gif/sticker/voice(waveform,speed)/audio/doc/contact/location/live-location/poll tombstone/edited/view-once states per reference doc sec 3.2. | Bubble type matrix | P1 | L | Track A |  | Partial | chat.tsx:3733-3838 image/video/gif/sticker/audio/file/poll/location; view-once 3716-3732 | No contact bubble (type 'contact' unhandled); voice has no playback-speed control | 2026-07-09 vs source
VC-087 | UI Elements | Chat screen | System bubbles | Day dividers, E2EE notice, group events, timer changes, key-change notices. | Center bubbles | P1 | S | Track A |  | Partial | chat.tsx:2054 DateChip day dividers; deleted tombstone 3584-3587 | No E2EE notice, group-event, timer-change, or key-change system bubbles | 2026-07-09 vs source
VC-088 | UI Elements | Chat screen | Long-press multi-select toolbar | Reply/copy/forward/star/pin/delete/report/info on selection. | Selection toolbar | P1 | M | Track A |  | Partial | chat.tsx:880-928 + components/MessageActionSheet.tsx:64-99 | Single-message long-press sheet, not a multi-select toolbar; no Report action | 2026-07-09 vs source
VC-089 | UI Elements | Chat screen | Message Info screen | Per-recipient delivered/read/played timestamps from receipts table. | Message info | P2 | S | Later |  | Partial | chat.tsx:2374-2410 Message-info modal (Read/Delivered/Sent buckets) | Modal not a screen; no per-recipient timestamps; no Played row | 2026-07-09 vs source
VC-090 | UI Elements | Chat screen | Swipe-to-reply gesture | Right swipe on bubble opens reply banner with quoted preview. | Swipe reply | P1 | S | Track A |  | Done | app/chat.tsx:2056 <SwipeToReply> wraps each bubble |  | 2026-07-09 vs source
VC-091 | UI Elements | Chat screen | Reaction picker + aggregation strip | Double-tap/long-press picker; counts under bubble; tap -> reactor list. | Reactions UI | P1 | M | Track A |  | Partial | chat.tsx:3880-3893 aggregation chips; picker 2342-2363 | No reactor-list (who-reacted) view | 2026-07-09 vs source
VC-092 | UI Elements | Composer | Full composer bar | Emoji/GIF/sticker panel, attach sheet (doc/camera/gallery/audio/location/contact/poll), send morph, reply banner. | Composer spec (doc 3.3) | P0 | L | Track A |  | Partial | chat.tsx:2210-2338 composer (emoji/GIF/attach/camera/mic-send morph); reply banner 2182-2208 | No sticker panel; attach sheet missing Contact and Audio | 2026-07-09 vs source
VC-093 | UI Elements | Composer | Voice note hold/lock/cancel recorder | Hold-to-record, slide-up lock, slide-left cancel; Opus/AAC encode -> media pipeline. | PTT recorder | P1 | M | Track E |  | Partial | chat.tsx:2216-2227 recording UI; mic start 2316-2324 | Tap-to-start (not hold-to-record); no slide-up lock / slide-left cancel gestures | 2026-07-09 vs source
VC-094 | UI Elements | Composer | @Mention autocomplete in groups | Member list popup on @; chips embedded as metadata. | Mention UI | P1 | S | Track A |  | Done | chat.tsx:766-780 autocomplete; 2121-2136 member popup; meta.mentions 804-805 | Rendered as colored tokens, not removable chips | 2026-07-09 vs source
VC-095 | UI Elements | Banners | Pinned message banner + unknown-contact safety banner | Pin banner with jump; Add/Block/Report banner for unknown senders. | Contextual banners | P2 | S | Later |  | Partial | chat.tsx:2011-2030 pinned-message banner (jump + unpin) | No unknown-contact safety banner (Add/Block/Report) | 2026-07-09 vs source
VC-096 | UI Elements | Media | Full-screen media viewer | Pinch zoom, swipe-down dismiss, left/right chronological media navigation, share/star/delete, All Media grid. | Media viewer spec | P1 | M | Track A |  | Partial | app/media-viewer.tsx:117-137 tap-zoom; share/save 255-256 | No pinch zoom, no swipe-down dismiss, no chronological prev/next, no star/delete, no All-Media grid | 2026-07-09 vs source
VC-097 | UI Elements | Media | Camera composer with edit tools | Capture, gallery strip, crop/draw/text/sticker/blur, HD toggle, caption + recipient chips, view-once toggle. | Camera composer | P2 | L | Track E |  | Partial | app/camera.tsx:143-145 view-once/modes; app/image-editor.tsx:280-282 crop/draw/text/filter | Separate screens not a unified composer; no sticker/blur; no HD toggle; no caption; no recipient chips | 2026-07-09 vs source
VC-098 | UI Elements | Status | Status rings + story viewer | Segmented rings viewed/unviewed, auto-advance progress bars, hold-pause, reply bar, viewer list. | Status viewer spec | P1 | L | Track F |  | Partial | status.tsx:254,418 segmented rings; story-viewer.tsx:312-337 pause/progress; 367-400 viewer list | No reply bar in the story viewer | 2026-07-09 vs source
VC-099 | UI Elements | Security | Safety-number verification screen | 60-digit code + QR from both identity keys; scan-to-verify; verified badge state. | Encryption row (doc sec 6) | P1 | M | Track F |  | Partial | app/verify-contact.tsx:108 60-digit safety number; verified badge 118-138 | No QR code rendering and no scan-to-verify flow | 2026-07-09 vs source
VC-100 | UI Elements | Settings | Settings tree parity | Account/Privacy/Chats/Notifications/Storage&Data screens per reference doc sec 7 (scoped to shipped features). | Settings tree | P1 | L | Later |  | Partial | app/settings.tsx:247-266 Chats, 268-324 Privacy, 340 Notifications | No Storage&Data section (storage-manager.tsx unlinked); no explicit Account header | 2026-07-09 vs source
VC-101 | UX | Perceived speed | Instant-send feel end-to-end | From tap to bubble <100ms regardless of network; all network states expressed via ticks not spinners. | UI never waits | P0 | M | Track A | Optimistic insert | Done | app/chat.tsx:808-824 pre-network bubble; ticks not spinners 3860-3870 |  | 2026-07-09 vs source
VC-102 | UX | Notifications | Rich grouped notifications | Group per chat, inline reply + mark-read actions, preview privacy setting, mention bypasses group mute. | Notification behavior | P0 | M | Track A |  | Partial | services/notificationService.ts:69,161-166; per-chat channels lib/push.ts:25-29 | No per-chat grouping/threadId, no inline reply / mark-read actions, no mention-bypasses-mute; preview privacy hardcoded | 2026-07-09 vs source
VC-103 | UX | Notifications | Per-chat custom tones + mute durations | 8h/1w/Always; custom sound per chat; stored locally. | Per-chat notification settings | P2 | S | Later |  | Partial | per-chat tones app/chat.tsx:1016-1029 setChatNotifSound | Mute is boolean (chatService.ts:1137); no 8h/1w/Always durations | 2026-07-09 vs source
VC-104 | UX | Voice | Consecutive voice-note autoplay + proximity earpiece | Auto-advance queued voice notes; proximity sensor switches speaker->earpiece. | Voice note UX | P2 | M | Later |  | Not Started | no proximity sensor or voice-note autoplay code | Absent | 2026-07-09 vs source
VC-105 | UX | Privacy UX | Read-receipt reciprocity | Disabling read receipts hides both directions (except groups). | Reciprocity rule | P1 | S | Track A |  | Partial | global toggle app/notifications.tsx:21; per-contact hideRead app/receipt-control.tsx:68-88 | No reciprocity enforcement (hide both directions) and no group exception | 2026-07-09 vs source
VC-106 | UX | Privacy UX | Disappearing messages timer | Off/24h/7d/90d; timer change is an E2EE control message; applies to new messages; local deletion job. | Disappearing messages | P1 | M | Track F |  | Partial | picker app/chat.tsx:1031-1055; setDisappearing chatService.ts:979; expires_at localDb.ts:74 | Sent as plain REST not an E2EE control message; NO local purge job (getCachedMessages never filters expires_at) | 2026-07-09 vs source
VC-107 | UX | Privacy UX | Chat lock + app lock (biometric) | Locked folder gated by biometric; app-level lock; local only. | Chat/app lock | P2 | M | Later |  | Done | lib/chatLock.ts:29-81 biometric+hashed PIN; app-lock gate app/index.tsx:22-23 |  | 2026-07-09 vs source
VC-108 | UX | Personalization | Per-chat wallpaper + theme | Global theme + per-chat override; Obsidian Aurora design tokens. | Chat theme/wallpaper | P3 | S | Later |  | Done | per-chat wallpaper app/chat.tsx:1852-1860; per-chat theme 2076 |  | 2026-07-09 vs source
VC-109 | UX | Reliability | Battery-exemption onboarding (OEM flows) | Guided whitelist flows for Xiaomi/Oppo/Vivo/Realme/Honor/Samsung; reuse call-reliability track work; critical for background delivery in India. | OEM battery workarounds | P0 | M | Track A |  | Done | lib/batteryOptimization.ts:36-153 OEM autostart + ignore-battery-opt; surfaced settings.tsx:341 | Reached from Settings/Call-reliability rather than a strict first-run onboarding | 2026-07-09 vs source
VC-110 | UX | Reliability | Full offline compose UX | Compose/queue anything offline; clear pending indicators; auto-flush on reconnect; airplane-mode test suite. | Offline-first behavior | P0 | M | Track A | Outbound queue | Partial | messageQueue.ts:84-107,212-228 persistent queue + auto-flush; pending bubbles chat.tsx:421-437 | Queue is TEXT-ONLY by design (messageQueue.ts:14-16); media/files are not offline-queued | 2026-07-09 vs source
VC-111 | UX | Reliability | Media retry/download affordances | Failed upload/download shows retry with size label; resumable. | Retry overlay | P1 | S | Track E |  | Partial | failed send retry chat.tsx:839-844; media retry :1435; size pill FileBubble :1549 | Media download not resumable (transferManager.ts unused for media); no size label on the download affordance | 2026-07-09 vs source
VC-112 | UX | Accessibility | Font scaling + a11y labels | System font scale respected in bubbles; TalkBack labels on all controls. | Font size setting | P2 | M | Later |  | Not Started | 0 matches for accessibilityLabel/accessibilityRole/allowFontScaling in app/*.tsx | No TalkBack labels; no deliberate bubble font-scaling handling | 2026-07-09 vs source